## Gantt Chart w % Complete
#REF!
DAYBREAK GANTT CHART
* = an automatically calculated cell
| TASK NAME | START DATE | DAY OF MONTH | END DATE | DURATION (WORK DAYS) | DAYS COMPLETE* | DAYS REMAINING* | TEAM MEMBER | PERCENT COMPLETE | Q1 | Q2 | Q3 | Q4
Concept Ideation
| Concept Ideation | 2023-08-28 | 28 | 2023-09-06 | 9 | 9 | 0 | All | 100%
| Market Research | 2023-08-29 | 29 | 2023-09-07 | 9 | 9 | 0 | Winston | 100%
| Gameplay Design | 2023-08-28 | 28 | 2023-10-30 | 63 | 56.7 | 6.3 | Winston | 100%
| Camera Movement | 2023-09-06 | 6 | 2023-10-16 | 40 | 40 | 0 | Winston | 100%
| Camera Interactions | 2023-09-06 | 6 | 2023-10-23 | 47 | 39.95 | 7.05 | Winston | 100%
| Destructable Environment | 2023-08-28 | 28 | 2023-11-16 | 80 | 80 | 0 | Winston | 30%
| Character Movement | 2023-09-06 | 6 | 2023-11-01 | 56 | 56 | 0 | Winston | 100%
| Technical Art Design | 2023-09-07 | 7 | 2023-11-17 | 71 | 56.8 | 14.2 | Jiaxu | 80%
| VFX Development | 2023-09-07 | 7 | 2023-11-17 | 71 | 56.8 | 14.2 | Jiaxu & Winston | 80%
| Level Design | 2023-09-05 | 5 | 2023-11-13 | 69 | 69 | 0 | XinYing | 100%
| Level Development | 2023-09-07 | 7 | 2023-11-13 | 67 | 63.65 | 3.35 | XinYing | 95%
| Environment Models | 2023-09-04 | 4 | 2023-11-13 | 70 | 70 | 0 | XinYing & John & Kerrin | 100%
| Character Design | 2023-09-04 | 4 | 2023-09-18 | 14 | 14 | 0 | XinYing & John | 100%
| 3D Character Modeling | 2023-09-04 | 4 | 2023-11-16 | 73 | 51.1 | 21.9 | Kerrin | 70%
| Integration | 2023-08-31 | 31 | 2023-11-16 | 77 | 69.3 | 7.7 | Winston & Jiaxu | 90%
| Concept Art | 2023-08-28 | 28 | 2023-11-16 | 80 | 80 | 0 | XinYing & John | 100%
| Inventory UI | 2023-09-11 | 11 | 2023-10-23 | 42 | 42 | 0 | Jiaxu & John | 100%
| Menu UI - Selection & Levels | 2023-09-12 | 12 | 2023-10-30 | 48 | 48 | 0 | Yokawa & Jiaxu | 100%
| Scene & Gameflow Development | 2023-09-13 | 13 | 2023-10-30 | 47 | 47 | 0 | Yokawa | 100%
Proof of Concept
| Player Inventory Backend | 2023-09-25 | 25 | 2023-11-08 | 44 | 44 | 0 | Winston | 100%
| Player Abilities Inplementation | 2023-09-22 | 22 | 2023-10-28 | 36 | 36 | 0 | Winston | 100%
| Combat | 2023-09-25 | 25 | 2023-11-15 | 51 | 40.8 | 10.2 | Winston | 80%
| Weapons & Damage Classes | 2023-09-25 | 25 | 2023-10-23 | 28 | 28 | 0 | Winston | 100%
| Object Classes | 2023-09-19 | 19 | 2023-10-02 | 13 | 13 | 0 | Winston | 100%
| Hierachy Inheritance | 2023-09-18 | 18 | 2023-09-22 | 4 | 4 | 0 | Winston | 100%
| AI Development | 2023-09-11 | 11 | 2023-11-13 | 63 | 56.7 | 6.3 | Winston | 90%
| AI States | 2023-09-11 | 11 | 2023-11-13 | 63 | 56.7 | 6.3 | Winston | 90%
| Environment Interaction Development | 2023-09-18 | 18 | 2023-10-12 | 24 | 24 | 0 | Winston | 100%
| Object Interaction Development | 2023-09-18 | 18 | 2023-10-18 | 30 | 30 | 0 | Winston | 100%
| Enemy Interaction Development | 2023-09-11 | 11 | 2023-11-13 | 63 | 53.55 | 9.45 | Winston | 85%
| Line of Sight(Player) | 2023-09-11 | 11 | 2023-09-14 | 3 | 0.9 | 2.1 | Winston | 100%
| Line of Sight(Enemy) | 2023-09-11 | 11 | 2023-09-17 | 6 | 6 | 0 | Winston | 100%
| Fog of War | 2023-09-14 | 14 | 2023-09-18 | 4 | 4 | 0 | Winston & Jiaxu | 100%
| UI/UX Design | 2023-09-25 | 25 | 2023-11-13 | 49 | 44.1 | 4.9 | Jiaxu & John | 90%
| UI/UX Development | 2023-09-25 | 25 | 2023-11-13 | 49 | 44.1 | 4.9 | Jiaxu | 90%
| Data Management - Data Tables | 2023-09-19 | 19 | 2023-10-16 | 27 | 27 | 0 | Jiaxu | 100%
| Audio Development - SFX | 2023-09-04 | 4 | 2023-11-13 | 70 | 63 | 7 | Jiaxu | 90%
| 3D Environment Texturing | 2023-09-12 | 12 | 2023-11-13 | 62 | 62 | 0 | XinYing & John | 100%
| 3D Weapon Modelling | 2023-09-12 | 12 | 2023-10-23 | 41 | 41 | 0 | XinYing | 100%
| 3D Prop Modelling | 2023-09-12 | 12 | 2023-10-23 | 41 | 41 | 0 | XinYing & John & Kerrin | 100%
| 3D Weapon Texturing | 2023-09-12 | 12 | 2023-11-13 | 62 | 62 | 0 | XinYing | 100%
| 3D Prop Texturing | 2023-09-12 | 12 | 2023-11-13 | 62 | 62 | 0 | XinYing & John & Kerrin | 100%
| 3D Environment Modeling | 2023-09-12 | 12 | 2023-11-13 | 62 | 62 | 0 | XinYing & John | 100%
| Game Manager Singletons | 2023-09-17 | 17 | 2023-10-23 | 36 | 35.64 | 0.36 | Yokawa | 99%
| Environmental Lighting | 2023-09-20 | 20 | 2023-11-07 | 48 | 48 | 0 | XinYing | 100%
Final Presentation
| Character Animator | 2023-09-18 | 18 | 2023-11-16 | 59 | 59 | 0 | Kerrin & XinYing | 100%
| Animation Integration & Blendspace | 2023-09-18 | 18 | 2023-11-16 | 59 | 59 | 0 | Kerrin | 100%
| 3D Character Texturing | 2023-11-16 | 16 | 2023-11-16 | 0 | 0 | 0 | Kerrin | 100%
| Polish | 2023-09-15 | 15 | 2023-11-16 | 62 | 49.6 | 12.4 | Winston & Jiaxu | 80%
| Objectives Development | 2023-10-17 | 17 | 2023-11-06 | 20 | 19 | 1 | Jiaxu & Yokawa | 95%
| Score System Development | 2023-09-18 | 18 | 2023-10-30 | 42 | 41.58 | 0.42 | Yokawa | 99%
| Play Testing | 2023-10-23 | 23 | 2023-11-16 | 24 | 9.6 | 14.4 | Winston | 40%
| Bug Fixing | 2023-09-15 | 15 | 2023-11-16 | 62 | 49.6 | 12.4 | Winston & Jiaxu | 80%
| Poster | 2023-11-08 | 15 | 2023-11-16 | 8 | 8 | 0 | XinYing & John | 100%
| Trailer Editing | 2023-11-15 | 15 | 2023-11-16 | 2 | 2 | 0 | XinYing & John | 100%
Proposal- 18th Sept
Proof of Concept - 9 Oct
Final- 17th Nov

## Basic Gantt Chart
GANTT CHART TEMPLATE
* = an automatically calculated cell
| TASK NAME | START DATE | END DATE | START ON DAY* | DURATION* (WORK DAYS) | TEAM MEMBER | PERCENT COMPLETE | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4
First Sample Project
| Write Landing Page Copy | 2018-01-05 | 2018-01-08 | 0 | 3 | Nathan | 100%
| Approve Page Copy | 2018-01-08 | 2018-01-11 | 3 | 3 | Meredith | 80%
| Review Landing Page Design | 2018-01-11 | 2018-01-16 | 6 | 5 | Brandon | 60%
| Build Landing Page | 2018-01-14 | 2018-01-19 | 9 | 5 | Michael | 40%
| Code Review Landing Page | 2018-01-17 | 2018-01-23 | 12 | 6 | Rachel | 20%
Second Sample Project
| Write Promotional Email | 2018-01-09 | 2018-01-12 | 4 | 3 | Nathan | 100%
| Design Promotional Email | 2018-01-12 | 2018-01-19 | 7 | 7 | Meredith | 80%
| Send Promotional Email | 2018-01-17 | 2018-01-19 | 12 | 2 | Brandon | 60%
| Analyze Campaign Results | 2018-01-22 | 2018-01-26 | 17 | 4 | Michael | 40%
Third Sample Project
| Plan Agenda for Meeting | 2018-01-15 | 2018-01-19 | 10 | 4 | Nathan | 100%
| Reserve Room | 2018-01-22 | 2018-01-23 | 17 | 1 | Meredith | 80%
| Finalize Presentation | 2018-01-22 | 2018-01-26 | 17 | 4 | Brandon | 60%
| Approve Presentation | 2018-01-26 | 2018-01-29 | 21 | 3 | Michael | 40%
| Create Invitations | 2018-01-22 | 2018-01-25 | 17 | 3 | Rachel | 20%
Fourth Sample Project
| Rewrite Online Calculator | 2018-01-15 | 2018-01-24 | 10 | 9 | Nathan | 100%
| Code Review Calculator | 2018-01-25 | 2018-01-30 | 20 | 5 | Meredith | 80%
| Update Messaging | 2018-01-24 | 2018-01-30 | 19 | 6 | Michael | 60%
| Publish Calculator | 2018-01-30 | 2018-01-31 | 25 | 1 | Rachel | 0%

## Manual Chart
GANTT CHART TEMPLATE
| TASK NAME | START DATE | END DATE | DURATION (WORK DAYS) | TEAM MEMBER | PERCENT COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F
First Sample Project
| Write Landing Page Copy | 2018-01-05 | 2018-01-08 | 3 | Nathan | 100%
|  |  |  | 0 | Meredith | 80% | bar: WEEK 2 M to WEEK 2 T
| Review Landing Page Design | 2018-01-11 | 2018-01-16 | 5 | Brandon | 60% | bar: WEEK 1 F to WEEK 2 Th
| Build Landing Page | 2018-01-14 | 2018-01-19 | 5 | Michael | 40% | bar: WEEK 2 T to WEEK 3 M
| Code Review Landing Page | 2018-01-17 | 2018-01-21 | 4 | Rachel | 20% | bar: WEEK 2 Th to WEEK 3 W
| Promote Landing Page | 2018-01-20 | 2018-01-23 | 3 | Annie | 10% | bar: WEEK 3 T to WEEK 3 Th
Second Sample Project
| Write Promotional Email | 2018-02-05 | 2018-02-08 | 3 | Nathan | 100%
| Design Promotional Email | 2018-02-08 | 2018-02-13 | 5 | Meredith | 80%
| Send Promotional Email to Contacts | 2018-02-11 | 2018-02-16 | 5 | Michael | 60%
| Analyze Results of Email Campagin | 2018-02-14 | 2018-02-23 | 9 | Annie | 40%
Third Sample Project
| Plan Agenda for Team Meeting | 2018-03-05 | 2018-03-08 | 3 | Rachel | 100%
| Reserve Room and Resources for Meeting | 2018-03-08 | 2018-03-13 | 5 | Michael | 80%
| Finalize Team Presentation | 2018-03-11 | 2018-03-16 | 5 | Brandon | 60%
| Review & Approve Presentation | 2018-03-14 | 2018-03-19 | 5 | Meredith | 40%
| Create Invitations for Meeting | 2018-03-17 | 2018-03-21 | 4 | Annie | 20%
| Setup Room for Meeting | 2018-03-20 | 2018-03-25 | 5 | Nathan | 10%
Fourth Sample Project
| Rewrite Code for Online Calculator | 2018-04-05 | 2018-04-08 | 3 | Nathan | 100%
| Code Review Updated Calculator | 2018-04-08 | 2018-04-10 | 2 | Meredith | 80%
| Update Messaging for Calculator | 2018-04-11 | 2018-04-16 | 5 | Michael | 60%
| Publish New Calculator to Site | 2018-04-14 | 2018-04-18 | 4 | Rachel | 40%