## Sheet1
|  | priority | acceptance criteria | owner
| As an strategy gamer, i want to explore tower paths, so that i can experiment with effective builds. | High | 8.1: Create unique tower 8.2: Create tower upgrade path 8.3: Create skill tree 8.4: Repeat for alot of Towers | designer
| As a person seeking challenge, i wish to have a ramping difficulty growth for harder challenges as the game progresses, so that i feel challenge growing over time. | High | 7.1: Create level multiplier 7.2: apply increasing multiplier to bloon stats 7.3: Increase spawn count for higher levels | developer
| As a competitive gamer, I want to see High damage numbers and overpower the enemy so that i can feel satisfied. | Low | 6.1: calculate damage values and related stats 6.2: Display damage values and related stats
| As a casual gamer, i want to have simple and intuitive controls so that i can get into the game quickly and spend less time going over basics. | Medium | 4.1: Create UI for controls 4.2: Have tutorial page for controls | designer
| As a person with short attention span, i want to be able to keep save files and return to them whenever i want. | Medium | 1.1: create save file 1.2: create ability to load save files | developer
| As a student, I want to play a game which I can play in the background so that i can focus on studying | Medium | 1.1 Create Option to autoplay at different speeds 1.2 Create option to disable music/sounds | designer
| As a poor person, i want a game that I am able to play on my low spec devices. | High | 9.1: Create low poly models that use little resources 9.2: Create mobile version of the game 9.3: Optimize build to ensure it can run on low spec devices | designer
| As a working adult, i want to play some less intense games so that i can relax from my work | Low | 2.1 Create the button to change the speed of the game 2.2 Create a button to play the next round when clicked 2.3 Create option to autostart levels | develper
| As a gamer, i want to feel more challenge when playing the same map | high | 17.1: Create different difficulties 17.2: Add more enemies in the harder difficulties 17.3: Make the harder enemies appear earlier | developer
| As a gamer I would like to be able to customise my UI to better suit me. | Medium | Program in game UI editor Implement the UI editor in the game | designer
| As an achiever, i want to discover and gain achievements to flaunt and show my hard work. | Low | 16.1: Create achievements 16.2: Track player progress along side gameplay 16.3: Unlock achievements when requirements are met 16.4 Display achievements on profile page | designer
| As a mobile gamer, I want a game that can crossplay so i can play with my friends on PC | High | 18.1: Make mobile and PC builds of the game 18.2: Implement crossplay support with people 18.3: Implement multiplayer support 18.4: Create servers to support multiplayer | Developer
| As a casual gamer, I want a game which reward hard work and effort, so that i can feel accomplished | Low | 19.1 Design awards that appear in the home page that the user can display 19.2 Design the icon to go to the achievements 19.3 Code out the achievements so that the user can get them | designer
| As a social gamer I would like to be able to play the game with my friends. | Medium | 20.1 Code LAN connection for 2-4 players' devices, with 1 root device 20.2 Allow for devices to send packets to each other 20.3 Allow for 1 player's phone to calculate for everybody 20.4 Design in game interactions and simple emote responses | developer
| As a gamer who values their time I want the game to have permanent rewards that makes me feel like spending time on the game was worth and the benefits that come with it. | Medium | 21.1 Create 3 different kinds of rewards: cosmetics, Heroes, Skills 21.2 Create In game currency to be earned over time 21.3 Allow players to unlock rewards with in game currency | designer
| As a casual gamer I want a system that would advise me what to do to beat the level. | Medium | Implement guide system for each level Implement shareable build order/placements | developer
| As a person who is colorblind I would like more accessibility options in the game. | Medium | Make art asset recolor Implement option to change in game | designer
| As a gamer who willingly spends money, I want a game which will allow me to get progress faster when i spend. | Low | 18.1: implement option to change in game 18.2: Plan out the different transactions that can be made | developer
| As a parent concerned for my child playing violent video games, I want a game that can provide entertainment to my child while also being family friendly. | Low | 20.1: Add a friendly tone to the game 20.2: Make sure that the game is family friendly | Designer
| As an Artist, i want to be able to create my own maps | Low | 10.1: Design the UI for map design 10.2: Create objects that Users can put on the map 10.3: Implement UI editor | Developer
Koh Win | goal: make base game |  |  |  |  | Winston | goal: create rewards for players
Sprint 1 | Task | Story Points | Hours | Owner |  | Sprint 2 | Task | Story Points | Hours | Owner
US1: Create Main Menu | 1.1 Main menu | 2 | 12 | Barry |  | US5: Achievements | 16.1: Create achievements | 4 | 6 | Barry
and Login Screen | 1.2 UI | 1 | 8 | Larry |  |  | 16.2: Track player progress along side gameplay |  | 6 | Kohwin
| 1.3 Settings | 2 | 8 | Barry |  |  | 16.3: Unlock achievements when requirements are met |  | 6 | Kohwin
| 1.4 Account Login | 2 | 8 | Winston |  |  | 16.4 Display achievements on profile page |  | 6 | Barry
| 1.5 Server side Account management | 3 | 12 | Winston |  | US6: Cross-platform | 18.1: Make mobile and PC builds of the game | 6 | 30 | Winston, Jerryl
| 1.6 Server to Client Communication | 3 | 14 | Koh Win |  |  | 18.2: Implement crossplay support through platforms |  | 6 | Winston
US2: Create Towers | 2.1 Create many unique towers | 3 | 14 | Anthony |  | US7: Multiplayer | 20.1 Code LAN connection for 2-4 players' devices, with 1 root device | 8 | 24 | Winston
and upgrade paths | 2.2 Create different upgrade path for towers | 2 | 12 | Koh Win |  |  | 20.2 Allow for devices to communicate locally |  | 12 | Anthony
| 2.2 Create Skill Tree | 2 | 10 | Anthony |  |  | 20.3 Design in game interactions and simple emote responses |  | 12 | Jerryl
US3: Increase Difficulty | 3.1 Create different bloons | 1 | 18 | Koh Win |  | US8: Profile display for awards and achievements | 19.1 Design awards that appear in the home page that the user can display | 4 | 6 | Larry
as game progresses | 3.2 Make some bloons have strength and weaknesses | 1 | 12 | Anthony |  |  | 19.2 Design the icon to go to the achievements |  | 6 | Larry
| 3.3 Add boss bloons | 2 | 12 | Anthony |  |  | 19.3 Code out the achievements so that the user can get them |  | 12 | Kohwin
| 3.4 Add level multiplier for bloon stats | 1 | 8 | Winston |  | US9: Ingame reward progression | 21.1 Create 3 different kinds of rewards: cosmetics, Heroes, Skills | 4 | 8 | Winston,Larry
US4:Create save progress | 4.1 Add save proccess | 1 | 4 | Barry |  |  | 21.2 Create In game currency to be earned over time |  | 6 | Larry
| 4.2 Connect save to backend Server | 2 | 6 | Barry and Larry |  |  | 21.3 Allow players to unlock rewards with in game currency |  | 10 | Winston
US5: Create Intuitive UI | 5.1 Design in game UI | 2 | 12 | Barry and Larry
| 5.2 Code game UI and buttons | 2 | 6 | Barry and Larry
| 5.3 Increase UI ease of access | 1 | 4 | Barry and Larry
Jerryl | goal: customization |  |  |  |  | Anthony | goal: Extra Features
Sprint 3 | Task | Story Points | Hours | Owner |  | Sprint 4 | Task | Story Points | Hours | Owner
US11: Play on low specs | 11.1: Create low poly models that use little resources | 10 | 30 | Barry, Larry, Jerryl |  | US16: Create Guide System | 16.1: Implement guide system for each level | 8 | 30 | Kohwin, Winston
| 11.2: Create mobile version of the game |  | 12 | Koh Win |  |  | 16.2: Implement shareable build order/placements |  | 18 | Kohwin
| 11.3: Optimize build to ensure it can run on low spec devices |  | 18 | Anthony, Larry |  | US17: Make the game more family friendly | 17.1: Modify assets to be more family friendly. | 5 | 24 | Barry, Larry
US12: As a gamer, i want to feel more challenge when playing the map | 17.1: Create different difficulties | 4 | 6 | Winston |  |  | 17.2: change in game |  | 6 | Barry
| 17.2: Add more enemies in the harder difficulties |  | 12 | Winston, Barry |  | US18: Create accesibillity options | 18.1: Make art asset recolor | 3 | 12 | Jerryl
| 17.3: Make the harder enemies appear earlier |  | 6 | Anthony |  |  | 18.2: implement option to change in game |  | 6 | Anthony
US13: Autoplaying game for concentration | 12.1 Create Option to autoplay at different speeds | 2 | 6 | Koh Win, |  | US19: Create Monetary transactions | 19.1: Plan out the different transactions that can be made | 3 | 12 | Larry
| 12.2 Create option to disable music/sounds |  | 6 | Winston |  |  | 19.2: Implement in game |  | 6 | Anthony
US14: Customise UI | 13.1: Program in game UI editor | 4 | 18 | Anthony,Jerryl |  | US20: Create Level Editor | 20.1: Design the UI for map design | 8 | 18 | Jerryl, Barry
| 13.2: Implement the UI editor in the game |  | 6 | Winston |  |  | 20.2: Create objects that Users can put on the map |  | 12 | Anthony
US15: Lifestyle improvements | 14.1 Create Option to autoplay at different speeds | 6 | 6 | Koh Win |  |  | 20.3: Implement UI editor |  | 18 | Anthony, Winston
| 14.2 Create option to disable music/sounds |  | 6 | Koh Win
| 14.2: Create Insta-towers that are already upgraded so you dont have to micro manage 24/ |  | 24 | Barry, Larry, Jerryl
156
Sprint 4
Story ID | Task | Hours | Owner | D1 Start | D1 Done | D2 Start | D2 Done | D3 Start | D3 Done | D4 Start | D4 Done | D5 Start | D5 Done
US16: Create Guide System | 16.1: Implement guide system for each level | 30 | Kohwin, Winston | 30 | 18 | 18 | 6 | 6 | 0 | 0 | 0 | 0 | 0
| 16.2: Implement shareable build order/placements | 18 | Kohwin | 18 | 18 | 18 | 12 | 12 | 6 | 6 | 0 | 0 | 0
US17: Make the game more family friendly | 17.1: Modify assets to be more family friendly. | 24 | Barry, Larry | 24 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 17.2: change in game | 6 | Barry | 6 | 6 | 6 | 6 | 6 | 0 | 0 | 0 | 0 | 0
US18: Create accesibillity options | 18.1: Make art asset recolor | 12 | Jerryl | 12 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 18.2: implement option to change in game | 6 | Anthony | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US19: Create Monetary transactions | 19.1: Plan out the different transactions that can be made | 12 | Larry | 12 | 12 | 12 | 12 | 12 | 6 | 6 | 0 | 0 | 0
| 19.2: Implement in game | 6 | Anthony | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 0 | 0 | 0
US20: Create Level Editor | 20.1: Design the UI for map editor | 18 | Jerryl, Barry | 18 | 18 | 18 | 18 | 18 | 12 | 12 | 0 | 0 | 0
| 20.2: Create objects that Users can put on the map | 12 | Anthony | 12 | 12 | 12 | 6 | 6 | 0 | 0 | 0 | 0 | 0
| 20.3: Implement UI editor | 18 | Anthony, Winston | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 12 | 12 | 0
Days | Hours | Velocity
Day 1 | 162 | 162 / 5 = 32.4 hours a day
Day 2 | 126
Day 3 | 90
Day 4 | 54
Day 5 | 18
Sprint 1
Story ID | Task | Hours | Owner | D1 Start | D1 Done | D2 Start | D2 Done | D3 Start | D3 Done | D4 Start | D4 Done | D5 Start | D5 Done
US1: UI | 1.1 Main menu | 12 | Barry | 12 | 4 | 8 | 2 | 6 | 6 | 0 | 0 | 0 | 0
| 1.2 UI | 8 | Larry | 8 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0
| 1.3 Settings | 8 | Barry | 8 | 0 | 8 | 2 | 6 | 4 | 2 | 2 | 0 | 0
| 1.4 Account Login | 8 | Winston | 8 | 6 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5 Server side Account management | 12 | Winston | 12 | 0 | 12 | 4 | 8 | 8 | 0 | 0 | 0 | 0
| 1.6 Server to Client Communication | 14 | Koh Win | 14 | 5 | 9 | 2 | 7 | 0 | 7 | 4 | 3 | 3
US2: Main mechanics | 2.1 Create many unique towers | 14 | Anthony | 14 | 6 | 8 | 5 | 3 | 3 | 0 | 0 | 0 | 0
| 2.2 Create different upgrade path for towers | 12 | Koh Win | 12 | 0 | 12 | 4 | 8 | 6 | 2 | 0 | 2 | 2
| 2.2 Create Skill Tree | 10 | Anthony | 10 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0
US3: Main Enemies and goal of game | 3.1 Create different bloons | 18 | Barry, Larry | 18 | 2 | 16 | 16 | 10 | 6 | 6 | 0 | 0 | 0
| 3.2 Make some bloons have strength and weaknesses | 12 | Anthony | 12 | 1 | 11 | 2 | 9 | 3 | 6 | 6 | 0 | 0
| 3.3 Add boss bloons | 12 | Anthony, Barry | 12 | 0 | 12 | 2 | 10 | 6 | 4 | 4 | 0 | 0
US4: save progress | 3.4 Add Multiplier for difficulty and bloons | 8 | Winston, Larry | 8 | 2 | 6 | 4 | 2 | 2 | 0 | 0 | 0 | 0
| 4.1 Add save proccess | 4 | Barry | 4 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0
| 4.2 Connect save to backend Server | 6 | Barry and Larry | 6 | 0 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0
| 5.1 Design in game UI | 12 | Barry and Larry | 12 | 4 | 8 | 2 | 6 | 6 | 0 | 0 | 0 | 0
US5: In game UI | 5.2 Code game UI and buttons | 6 | Barry and Larry | 6 | 0 | 6 | 0 | 6 | 2 | 4 | 2 | 2 | 2
| 5.3 Increase UI ease of access | 4 | Barry and Larry | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Days | Hours | Velocity
Day 1 | 180 | 200/5 = 40 hours / day
Day 2 | 135
Day 3 | 81
Day 4 | 31
Day 5 | 7
Burndown chart
Sprint 2
Story ID | Task | Hours | Owner | D1 Start | D1 Done | D2 Start | D2 Done | D3 Start | D3 Done | D4 Start | D4 Done | D5 Start | D5 Done
US5: Achievements | 16.1: Create achievements | 6 | Barry | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 16.2: Track player progress along side gameplay | 6 | Kohwin | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 16.3: Unlock achievements when requirements are met | 6 | Kohwin | 6 | 0 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0
| 16.4 Display achievements on profile page | 6 | Barry | 6 | 0 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0
US8: Profile display for awards and achievements | 19.1 Design awards that appear in the home page that the user can display | 6 | Larry | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 19.2 Design the icon to go to the achievements | 6 | Larry | 6 | 0 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0
| 19.3 Code out the achievements so that the user can get them | 12 | Kohwin | 12 | 0 | 12 | 0 | 12 | 6 | 6 | 6 | 0 | 0
US6: Cross-platform | 18.1: Make mobile and PC builds of the game | 30 | Winston, Jerryl | 30 | 6 | 24 | 6 | 18 | 6 | 12 | 6 | 6 | 6
| 18.2: Implement crossplay support through platforms | 6 | Winston | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US7: Multiplayer | 20.1 Code LAN connection for 2-4 players' devices, with 1 root device | 24 | Winston | 24 | 0 | 24 | 0 | 24 | 6 | 12 | 6 | 6 | 6
| 20.2 Allow for devices to communicate locally | 12 | Anthony | 12 | 6 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0
| 20.3 Design in game interactions and simple emote responses | 12 | Jerryl | 12 | 0 | 12 | 0 | 6 | 6 | 0 | 0 | 0 | 0
US9: Ingame reward progression | 21.1 Create 3 different kinds of rewards: cosmetics, Heroes, Skills | 8 | Winston,Larry | 8 | 0 | 8 | 0 | 4 | 0 | 4 | 4 | 0 | 0
| 21.2 Create In game currency to be earned over time | 6 | Larry | 6 | 0 | 6 | 0 | 6 | 6 | 0 | 0 | 0 | 0
| 21.3 Allow players to unlock rewards with in game currency | 10 | Winston | 10 | 0 | 10 | 6 | 4 | 4 | 0 | 0 | 0 | 0
Days | Hours | Velocity
Day 1 | 156 | 36 | Hours per day
Day 2 | 120 | 36 | Hours per day
Day 3 | 74 | 34 | Hours per day
Day 4 | 34 | 22 | Hours per day
Day 5 | 12 | 12 | Hours per day
Sprint 3
Story ID | Task | Hours | Owner | D1 Start | D1 Done | D2 Start | D2 Done | D3 Start | D3 Done | D4 Start | D4 Done | D5 Start | D5 Done
US11: Play on low specs | 11.1: Create low poly models that use little resources | 30 | Barry, Larry, Jerryl | 30 | 18 | 12 | 12(Barry, Jerryl) | 0 | 0 | 0 | 0 | 0 | 0
| 11.2: Create mobile version of the game | 12 | Koh Win | 12 | 6 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0
| 11.3: Optimize build to ensure it can run on low spec devices | 18 | Anthony, Larry | 18 | 12 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0
US12: As a gamer, i want to | 12.1: Create different difficulties | 6 | Winston | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
feel more challenge when playing the map | 12.2: Add more enemies in the harder difficulties | 12 | Winston,Barry | 12 | 0 | 12 | 6 | 6 | 6(Barry) | 0 | 0 | 0 | 0
| 12.3: Make the harder enemies appear earlier | 6 | Anthony | 6 | 0 | 6 | 0 | 6 | 6 | 0 | 0 |  | 0
US13: Autoplaying game | 13.1 Create Option to autoplay at different speeds | 6 | Koh Win, | 6 | 0 | 6 | 0 | 6 | 6 | 0 | 0 | 0 | 0
for concentration | 13.2 Create option to disable music/sounds | 6 | Winston | 6 | 0 | 6 | 0 | 6 | 6 | 0 | 0 | 0 | 0
US14: Customise UI | 14.1: Program in game UI editor | 18 | Anthony, Jerryl | 18 | 0 | 18 | 0 | 18 | 6(Jerryl) | 12 | 12 | 0 | 0
| 14.2: Implement the UI editor in the game | 6 | Winston | 6 | 0 | 6 | 0 | 6 | 0 | 6 | 6 | 0 | 0
US15: Lifestyle improvements | 15.1 Create Option to autoplay at different speeds | 6 | Koh Win | 6 | 0 | 6 | 0 | 6 | 0 | 6 | 6 | 0 | 0
| 15.2 Create option to disable music/sounds | 6 | Koh Win, | 6 | 0 | 6 | 0 | 6 | 0 | 6 | 0 | 6 | 6
| 15.3: Create Insta-towers that are already upgraded so you dont have to micro manage 24/ | 24 | Jerryl, Barry, Larry, Winston | 24 | 0 | 24 | 0 | 24 | 0 | 24 | 12 | 12 | 12
|  | 156 |  | 156 | 42 | 120 | 36 | 84 | 30 | 54 | 36 | 18 | 18
Days | Hours | Velocity
Day1 | 156 | 156/5 = 31.2
Day2 | 120
Day3 | 84
Day4 | 54
Day5 | 18
s

## Sheet2
Sprint 1 | Task | Story Points | Hours | Owner | Sprint 2 | Task | Story Points | Hours | Owner
US1: Create Main Menu and login screen | 1.1 Main menu | 10 | 12 | Barry | US6: Achievements | 16.1: Create achievements | 4 | 6 | Barry
| 1.2 UI |  | 8 | Larry |  | 16.2: Track player progress along side gameplay |  | 6 | Kohwin
| 1.3 Settings |  | 8 | Barry |  | 16.3: Unlock achievements when requirements are met |  | 6 | Kohwin
| 1.4 Account Login |  | 8 | Winston |  | 16.4 Display achievements on profile page |  | 6 | Barry
| 1.5 Server side Account management |  | 12 | Winston | US7: Cross-platform | 18.1: Make mobile and PC builds of the game | 6 | 30 | Winston, Jerryl
| 1.6 Server to Client Communication |  | 14 | Koh Win |  | 18.2: Implement crossplay support through platforms |  | 6 | Winston
US2: Create Towers and upgrade paths | 2.1 Create many unique towers | 7 | 14 | Anthony | US8: Multiplayer | 20.1 Code LAN connection for 2-4 players' devices, with 1 root device | 8 | 24 | Winston
| 2.2 Create different upgrade path for towers |  | 12 | Koh Win |  | 20.2 Allow for devices to communicate locally |  | 12 | Anthony
| 2.2 Create Skill Tree |  | 10 | Anthony |  | 20.3 Design in game interactions and simple emote responses |  | 12 | Jerryl
US3: Increase Difficulty as game progresses | 3.1 Create different bloons | 5 | 18 | Koh Win | US9: Profile display for awards and achievements | 19.1 Design awards that appear in the home page that the user can display | 4 | 6 | Larry
| 3.2 Make some bloons have strength and weaknesses |  | 12 | Anthony |  | 19.2 Design the icon to go to the achievements |  | 6 | Larry
| 3.3 Add boss bloons |  | 12 | Anthony |  | 19.3 Code out the achievements so that the user can get them |  | 12 | Kohwin
| 3.4 Add level multiplier for bloon stats |  | 8 | Winston | US10: Ingame reward progression | 21.1 Create 3 different kinds of rewards: cosmetics, Heroes, Skills | 4 | 8 | Winston,Larry
US4:Create save progress | 4.1 Add save proccess | 3 | 4 | Barry |  | 21.2 Create In game currency to be earned over time |  | 6 | Larry
| 4.2 Connect save to backend Server |  | 6 | Barry, Larry |  | 21.3 Allow players to unlock rewards with in game currency |  | 10 | Winston
US5: Create Intuitive UI | 5.1 Design in game UI | 5 | 12 | Barry, Larry |  |  | 26
| 5.2 Code game UI and buttons |  | 6 | Barry, Larry
| 5.3 Increase UI ease of access |  | 4 | Barry, Larry
30
| Jerryl |  |  |  | Anthony
Sprint 3 | Task | Story Points | Hours | Owner | Sprint 4 | Task | Story Points | Hours | Owner
US11: Play on low specs | 11.1: Create low poly models that use little resources | 9 | 30 | Barry, Larry, Jerryl | US16: Create Guide System | 16.1: Implement guide system for each level | 8 | 30 | Kohwin, Winston
| 11.2: Create mobile version of the game |  | 12 | Koh Win |  | 16.2: Implement shareable build order/placements |  | 18 | Kohwin
| 11.3: Optimize build to ensure it can run on low spec devices |  | 18 | Anthony, Larry | US17: Make the game more family friendly | 17.1: Modify assets to be more family friendly. | 5 | 24 | Barry, Larry
US12: As a gamer, i want to feel more challenge when playing the map | 17.1: Create different difficulties | 3 | 6 | Winston |  | 17.2: change in game |  | 6 | Barry
| 17.2: Add more enemies in the harder difficulties |  | 12 | Winston, Barry | US18: Create accesibillity options | 18.1: Make art asset recolor | 3 | 12 | Jerryl
| 17.3: Make the harder enemies appear earlier |  | 6 | Anthony |  | 18.2: implement option to change in game |  | 6 | Anthony
US13: Autoplaying game for concentration | 12.1 Create Option to autoplay at different speeds | 2 | 6 | Koh Win, | US19: Create Monetary transactions | 19.1: Plan out the different transactions that can be made | 3 | 12 | Larry
| 12.2 Create option to disable music/sounds |  | 6 | Winston |  | 19.2: Implement in game |  | 6 | Anthony
US14: Customise UI | 13.1: Program in game UI editor | 4 | 18 | Anthony,Jerryl | US20: Create Level Editor | 20.1: Design the UI for map design | 8 | 18 | Jerryl, Barry
| 13.2: Implement the UI editor in the game |  | 6 | Winston |  | 20.2: Create objects that Users can put on the map |  | 12 | Anthony
US15: Lifestyle improvements | 14.1 Create Option to autoplay at different speeds | 6 | 6 | Koh Win |  | 20.3: Implement UI editor |  | 18 | Anthony, Winston
| 14.2 Create option to disable music/sounds |  | 6 | Koh Win |  |  | 27
| 14.2: Create Insta-towers that are already upgraded so you dont have to micro manage 24/ |  | 24 | Barry, Larry, Jerryl
24

## Sprint 1
Sprint 1 | Koh Win
Story ID | Task | Hours | Owner | D1 Start | D1 Done | D2 Start | D2 Done | D3 Start | D3 Done | D4 Start | D4 Done | D5 Start | D5 Done
US1: UI | 1.1 Main menu | 12 | Barry | 12 | 4 | 8 | 2 | 6 | 6 | 0 | 0 | 0 | 0
| 1.2 UI | 8 | Larry | 8 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0
| 1.3 Settings | 8 | Barry | 8 | 0 | 8 | 2 | 6 | 4 | 2 | 2 | 0 | 0
| 1.4 Account Login | 8 | Winston | 8 | 6 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5 Server side Account management | 12 | Winston | 12 | 0 | 12 | 4 | 8 | 8 | 0 | 0 | 0 | 0
| 1.6 Server to Client Communication | 14 | Koh Win | 14 | 5 | 9 | 2 | 7 | 0 | 7 | 4 | 3 | 3
US2: Main mechanics | 2.1 Create many unique towers | 14 | Anthony | 14 | 6 | 8 | 5 | 3 | 3 | 0 | 0 | 0 | 0
| 2.2 Create different upgrade path for towers | 12 | Koh Win | 12 | 0 | 12 | 4 | 8 | 6 | 2 | 0 | 2 | 2
| 2.2 Create Skill Tree | 10 | Anthony | 10 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0
US3: Main Enemies and goal of game | 3.1 Create different bloons | 18 | Barry, Larry | 18 | 2 | 16 | 6 | 10 | 4 | 6 | 6 | 0 | 0
| 3.2 Make some bloons have strength and weaknesses | 12 | Anthony | 12 | 1 | 11 | 2 | 9 | 3 | 6 | 6 | 0 | 0
| 3.3 Add boss bloons | 12 | Anthony, Barry | 12 | 0 | 12 | 2 | 10 | 6 | 4 | 4 | 0 | 0
US4: save progress | 3.4 Add Multiplier for difficulty and bloons | 8 | Winston, Larry | 8 | 2 | 6 | 4 | 2 | 2 | 0 | 0 | 0 | 0
| 4.1 Add save proccess | 4 | Barry | 4 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0
| 4.2 Connect save to backend Server | 6 | Barry and Larry | 6 | 0 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0
| 5.1 Design in game UI | 12 | Barry and Larry | 12 | 4 | 8 | 2 | 6 | 6 | 0 | 0 | 0 | 0
US5: In game UI | 5.2 Code game UI and buttons | 6 | Barry and Larry | 6 | 0 | 6 | 0 | 6 | 2 | 4 | 2 | 2 | 2
| 5.3 Increase UI ease of access | 4 | Barry and Larry | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Days | Hours | Velocity
Day 1 | 180 | 30 hours / sprint
Day 2 | 135
Day 3 | 81
Day 4 | 31
Day 5 | 7
Daily Meeting Notes
Day 1 | Day 1, I Got started on the Main menu , got good progress on that. Did a touch of save progress until larry required help for coding the in game Ui. Ill continue doing the main menu tomorrow, start on the settings and probably help out larry a little more. There is a bug with the settings where it doesnt display if you change your aspect ratio. - Barry
Day 2 | Day 2, i spent most of my day fixing server side issues and trying to get this login system to function. Then Larry needed help so i did the miltiplier with him for a bit. Will try an finish fixing server issues tomorrow. - Winston
Day3 | Day 3, Spent the entire day working on boss bloons and their multipliers with Barry. I will move on to making them have strengths and weaknesses tomorrow. Found out a bug where the 2nd boss will not spawn the correct amount of bloons when killed on the hard difficulty specifically. - Anthony
Day 4 | Day 4, Finally finished the settings and different bloon types. Now all thats left is the UI button coding. It shouldnt take too long. - Barry
Day 5 | Day 5, Touched up on the client to server side communication and creating different upgrade paths for towers.

## Sprint 2
Sprint 2
Story ID | Task | Hours | Owner | D1 Start | D1 Done | D2 Start | D2 Done | D3 Start | D3 Done | D4 Start | D4 Done | D5 Start | D5 Done
US5: Achievements | 16.1: Create achievements | 6 | Barry | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 16.2: Track player progress along side gameplay | 6 | Kohwin | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 16.3: Unlock achievements when requirements are met | 6 | Kohwin | 6 | 0 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0
| 16.4 Display achievements on profile page | 6 | Barry | 6 | 0 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0
US8: Profile display for awards and achievements | 19.1 Design awards that appear in the home page that the user can display | 6 | Larry | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 19.2 Design the icon to go to the achievements | 6 | Larry | 6 | 0 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0
| 19.3 Code out the achievements so that the user can get them | 12 | Kohwin | 12 | 0 | 12 | 0 | 12 | 6 | 6 | 6 | 0 | 0
US6: Cross-platform | 18.1: Make mobile and PC builds of the game | 30 | Winston, Jerryl | 30 | 6 | 24 | 6 | 18 | 6 | 12 | 6 | 6 | 6
| 18.2: Implement crossplay support through platforms | 6 | Winston | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US7: Multiplayer | 20.1 Code LAN connection for 2-4 players' devices, with 1 root device | 24 | Winston | 24 | 0 | 24 | 0 | 24 | 6 | 12 | 6 | 6 | 6
| 20.2 Allow for devices to communicate locally | 12 | Anthony | 12 | 6 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0
| 20.3 Design in game interactions and simple emote responses | 12 | Jerryl | 12 | 0 | 12 | 0 | 6 | 6 | 0 | 0 | 0 | 0
US9: Ingame reward progression | 21.1 Create 3 different kinds of rewards: cosmetics, Heroes, Skills | 8 | Winston,Larry | 8 | 0 | 8 | 0 | 4 | 0 | 4 | 4 | 0 | 0
| 21.2 Create In game currency to be earned over time | 6 | Larry | 6 | 0 | 6 | 0 | 6 | 6 | 0 | 0 | 0 | 0
| 21.3 Allow players to unlock rewards with in game currency | 10 | Winston | 10 | 0 | 10 | 6 | 4 | 4 | 0 | 0 | 0 | 0
Days | Hours | Velocity
Day 1 | 156 | 36 | Hours per day
Day 2 | 120 | 36 | Hours per day
Day 3 | 74 | 34 | Hours per day
Day 4 | 34 | 22 | Hours per day
Day 5 | 12 | 12 | Hours per day

## Sprint 3
Sprint 3
Story ID | Task | Hours | Owner | D1 Start | D1 Done | D2 Start | D2 Done | D3 Start | D3 Done | D4 Start | D4 Done | D5 Start | D5 Done
US11: Play on low specs | 11.1: Create low poly models that use little resources | 30 | Barry, Larry, Jerryl | 30 | 18 | 12 | 12(Barry, Jerryl) | 0 | 0 | 0 | 0 | 0 | 0
| 11.2: Create mobile version of the game | 12 | Koh Win | 12 | 6 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0
| 11.3: Optimize build to ensure it can run on low spec devices | 18 | Anthony, Larry | 18 | 12 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0
US12: As a gamer, i want to feel more challenge when playing the map | 12.1: Create different difficulties | 6 | Winston | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 12.2: Add more enemies in the harder difficulties | 12 | Winston,Barry | 12 | 0 | 12 | 6 | 6 | 6(Barry) | 0 | 0 | 0 | 0
| 12.3: Make the harder enemies appear earlier | 6 | Anthony | 6 | 0 | 6 | 0 | 6 | 6 | 0 | 0 |  | 0
US13: Autoplaying game for concentration | 13.1 Create Option to autoplay at different speeds | 6 | Koh Win, | 6 | 0 | 6 | 0 | 6 | 6 | 0 | 0 | 0 | 0
| 13.2 Create option to disable music/sounds | 6 | Winston | 6 | 0 | 6 | 0 | 6 | 6 | 0 | 0 | 0 | 0
US14: Customise UI | 14.1: Program in game UI editor | 18 | Anthony, Jerryl | 18 | 0 | 18 | 0 | 18 | 6(Jerryl) | 12 | 12 | 0 | 0
| 14.2: Implement the UI editor in the game | 6 | Winston | 6 | 0 | 6 | 0 | 6 | 0 | 6 | 6 | 0 | 0
US15: Lifestyle improvements | 15.1 Create Option to autoplay at different speeds | 6 | Koh Win | 6 | 0 | 6 | 0 | 6 | 0 | 6 | 6 | 0 | 0
| 15.2 Create option to disable music/sounds | 6 | Koh Win, | 6 | 0 | 6 | 0 | 6 | 0 | 6 | 0 | 6 | 6
| 15.3: Create Insta-towers that are already upgraded so you dont have to micro manage 24/ | 24 | Jerryl, Barry, Larry, Winston | 24 | 0 | 24 | 0 | 24 | 0 | 24 | 12 | 12 | 12
|  | 156 |  | 156 | 42 | 120 | 36 | 84 | 30 | 54 | 36 | 18 | 18
Days | Hours | Velocity
Day1 | 156 | 156/5 = 31.2
Day2 | 120
Day3 | 84
Day4 | 54
Day5 | 18
Daily Stand Meeting Notes
Day2: The previous day, i designed some of the low poly models with Larry and Barry, later i am going to finish the low poly models together with Barry. There were no problems so far. -Jerryl
Day3: The previous day i spent the day optimising the build with Larry to run on low spec devices, later i am going to program the game so harder enemies appear in different difficulties. So far i have no issues faced. - Anthony
Day4: I was sick so i couldnt do anything the previous day, I am going to help create insta-towers with Barry, Larry and Winston. - Larry
Day5: I was coding in and testing the option to autoplay at different speeds, today i will create and test the option to disable musics and all sounds. There was a small problem which made me spend more time than needed on it but it was fixed and done - Koh Win
13

## Sprint 4
Sprint 4
Story ID | Task | Hours | Owner | D1 Start | D1 Done | D2 Start | D2 Done | D3 Start | D3 Done | D4 Start | D4 Done | D5 Start | D5 Done
US16: Create Guide System | 16.1: Implement guide system for each level | 30 | Kohwin, Winston | 30 | 18 | 18 | 6 | 6 | 0 | 0 | 0 | 0 | 0
| 16.2: Implement shareable build order/placements | 18 | Kohwin | 18 | 18 | 18 | 12 | 12 | 6 | 6 | 0 | 0 | 0
US17: Make the game more family friendly | 17.1: Modify assets to be more family friendly. | 24 | Barry, Larry | 24 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 17.2: change in game | 6 | Barry | 6 | 6 | 6 | 6 | 6 | 0 | 0 | 0 | 0 | 0
US18: Create accesibillity options | 18.1: Make art asset recolor | 12 | Jerryl | 12 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 18.2: implement option to change in game | 6 | Anthony | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US19: Create Monetary transactions | 19.1: Plan out the different transactions that can be made | 12 | Larry | 12 | 12 | 12 | 12 | 12 | 6 | 6 | 0 | 0 | 0
| 19.2: Implement in game | 6 | Anthony | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 0 | 0 | 0
US20: Create Level Editor | 20.1: Design the UI for map editor | 18 | Jerryl, Barry | 18 | 18 | 18 | 18 | 18 | 12 | 12 | 0 | 0 | 0
| 20.2: Create objects that Users can put on the map | 12 | Anthony | 12 | 12 | 12 | 6 | 6 | 0 | 0 | 0 | 0 | 0
| 20.3: Implement UI editor | 18 | Anthony, Winston | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 12 | 12 | 0
Days | Hours | Velocity
Day 1 | 162 | 162 / 5 = 32.4 hours a day
Day 2 | 126
Day 3 | 90
Day 4 | 54
Day 5 | 18
Daily Stand Meeting Notes
Day
day 1
day 2
day 3
day 4